## WBS Dictionary
WBS ID | Branch | Work Package | Hours | Week | Depends On | Completion Criterion | Plan Ref | Critical Path | Status | % Complete
1.1.1 | 1.0 | Project charter | 2 | 0 | - | Scope, problem, success criteria approved | - | N | Not started | 0%
1.1.2 | 1.0 | Technical design specification | 2 | 0 | 1.1.1 | Architecture, schemas, algorithms documented | - | N | Not started | 0%
1.1.3 | 1.0 | WBS & schedule | 1 | 0 | 1.1.2 | All work decomposed; critical path identified | - | N | Not started | 0%
1.2.1 | 1.0 | Risk register maintenance | 2 | 1-6 | 1.1.3 | Reviewed and dated every Monday | - | N | Not started | 0%
1.2.2 | 1.0 | Cost guardrails & budget alarms | 1 | 1 | 3.1.1 | Alerts at $10/$25/$50 firing; egress alarm set | T2 | N | Not started | 0%
1.2.3 | 1.0 | Weekly progress log | 1 | 1-6 | - | 6 dated entries: cost, volume, event rate | - | N | Not started | 0%
1.3.1 | 1.0 | Data governance & ethics policy | 1 | 0 | - | Publishable without edits | - | N | Not started | 0%
1.3.2 | 1.0 | robots.txt re-verification | 0 | 1-6 | 1.3.1 | Matrix re-checked weekly; changes logged | - | N | Not started | 0%
2.1.1 | 2.0 | Repo skeleton & config loader | 2 | 1 | - | pytest tests/test_smoke.py green | T1 | N | Not started | 0%
2.1.2 | 2.0 | Source definitions (4 portals) | 1 | 1 | 2.1.1 | 4 sources with sitemaps and URL patterns | T1 | N | Not started | 0%
2.1.3 | 2.0 | Crawl frontier (SQLite, panel-aware) | 4 | 1 | 2.1.1 | 5 frontier tests green; 2-failure rule verified | T4 | Y | Not started | 0%
2.1.4 | 2.0 | Sitemap poller with index recursion | 2 | 1 | 2.1.3 | Returns >=10k URLs for one live source | T5 | N | Not started | 0%
2.2.2 | 2.0 | Scrapy spider - batdongsan | 6 | 1 | 2.1.3, 2.2.4 | BRONZE OBJECTS LANDING IN S3 (Sep 18) | T6 | Y | Not started | 0%
2.2.3 | 2.0 | Scrapy spiders - phongtro123, mogi, nhatot | 5 | 1 | 2.2.2 | 4 source= prefixes in today's partition | T7 | N | Not started | 0%
2.2.4 | 2.0 | S3 bronze batch writer | 2 | 1 | 2.1.1 | Writer test green; ~128 MB parts | T6 | Y | Not started | 0%
2.3.1 | 2.0 | Provisional cohort freeze (Sep 20) | 0.5 | 1 | 2.2.2 | ~50k listings flagged in_panel | T8 | N | Not started | 0%
2.3.2 | 2.0 | Full cohort freeze, stratified (Sep 25) | 1 | 2 | 2.2.3 | ~200k, stratified by source x province | T12 | Y | Not started | 0%
2.3.3 | 2.0 | Daily liveness probe scheduler | 2.5 | 2 | 2.3.2 | Soft-delete detection tested; 2 days landed | T12 | Y | Not started | 0%
2.4.1 | 2.0 | EC2 deployment & cron scheduling | 1 | 1 | 2.2.2 | Unattended run across a full day | T6 | Y | Not started | 0%
2.4.2 | 2.0 | Throughput validation & monitoring | 0 | 1 | 2.4.1 | >=2,000 pages/hour sustained | T6 | N | Not started | 0%
3.1.1 | 3.0 | S3 bucket, prefixes, lifecycle rules | 1.5 | 1 | - | Public access blocked; prefixes created | T2 | N | Not started | 0%
3.1.2 | 3.0 | Glue Data Catalog & Athena setup | 1 | 3 | 4.1.3 | Silver queryable via Athena | T15 | N | Not started | 0%
3.2.1 | 3.0 | Oracle Always Free VM provisioning (3 nodes) | 2.5 | 2 | - | 3 VMs running; ports open in VCN only | T10 | N | Not started | 0%
3.2.2 | 3.0 | Spark 3.5 standalone install + S3A connector | 5 | 2 | 3.2.1 | 2 workers ALIVE; smoke_s3.py returns a count | T10 | N | Not started | 0%
3.2.3 | 3.0 | Job submission tooling (submit.sh) | 1 | 2 | 3.2.2 | submit.sh runs a job end to end | T10 | N | Not started | 0%
3.3.1 | 3.0 | Docker HDFS/YARN demo cluster (optional) | 1 | 3 | 3.2.2 | NameNode + ResourceManager screenshots | T10 | N | Not started | 0%
4.1.1 | 4.0 | Parser ABC & Vietnamese normalisation | 4 | 1 | 2.1.1 | 13 normalisation tests green | T3 | N | Not started | 0%
4.1.2 | 4.0 | Four source parsers + HTML fixtures | 5 | 2 | 4.1.1 | 8 parser tests green; property types mapped | T3,T7 | N | Not started | 0%
4.1.3 | 4.0 | Spark bronze->silver parse job | 5 | 2 | 4.1.2, 3.2.3 | Idempotency test green; silver written | T9 | Y | Not started | 0%
4.2.1 | 4.0 | PII stripping & automated leak gate | 2 | 2 | 4.1.3 | Audit query returns 0 | T9 | N | Not started | 0%
4.2.2 | 4.0 | Schema, range & parse-rate assertions | 2 | 2 | 4.1.3 | Job fails loudly; parse rate >=95% | T9 | N | Not started | 0%
4.3.1 | 4.0 | MinHash LSH dedup & canonicalisation | 4 | 2 | 4.1.3 | 20 clusters validated; rate 10-25% | T11 | Y | Not started | 0%
4.4.1 | 4.0 | Panel fact table (listing x day) | 1.5 | 3 | 4.3.1, 2.3.3 | One row per listing per day | T13 | Y | Not started | 0%
4.4.2 | 4.0 | Right-censored survival labelling | 1.5 | 3 | 4.4.1 | Censoring test green; 1 absence != event | T13 | Y | Not started | 0%
5.1.1 | 5.0 | OSM POI extraction (Overpass) | 2 | 3 | - | osm_pois.parquet cached | T14 | N | Not started | 0%
5.1.2 | 5.0 | H3 indexing & proximity features | 3 | 3 | 5.1.1, 4.1.3 | H3 tests green; null coords handled | T14 | N | Not started | 0%
5.2.1 | 5.0 | Market structure notebook | 3 | 3 | 4.3.1 | Distributions, missingness, duplicate rates | T15 | N | Not started | 0%
5.2.2 | 5.0 | Geographic analysis & choropleth maps | 3 | 3 | 5.1.2 | Choropleth + hexbin + distance-to-CBD fit | T15 | N | Not started | 0%
5.2.3 | 5.0 | Temporal analysis & Kaplan-Meier curves | 2 | 3 | 4.4.2 | KM by price quintile - the thesis figure | T15 | N | Not started | 0%
5.3.1 | 5.0 | Report-quality figure set (300 dpi) | 2 | 3 | 5.2.1 | All figures exported to reports/figures/ | T15 | N | Not started | 0%
6.1.1 | 6.0 | Feature engineering (numeric/geo/text/amenity) | 4 | 4 | 5.1.2, 4.3.1 | features_rent written | T17 | N | Not started | 0%
6.1.2 | 6.0 | Leakage-safe temporal split | 2 | 4 | 6.1.1 | Cluster-leak test green | T17 | Y | Not started | 0%
6.2.1 | 6.0 | District-median baseline | 1 | 4 | 6.1.2 | Baseline MAPE recorded | T18 | N | Not started | 0%
6.2.2 | 6.0 | GBT regressor training & evaluation | 5 | 4 | 6.2.1 | MAPE by province and price decile | T18 | N | Not started | 0%
6.2.3 | 6.0 | Hyperparameter tuning (CrossValidator) | 4 | 4 | 6.2.2 | MAPE <=20%, >=30% better than baseline | T18 | N | Not started | 0%
6.2.4 | 6.0 | price_gap scoring across all listings | 1 | 4 | 6.2.3 | features_survival carries price_gap | T18 | Y | Not started | 0%
6.3.1 | 6.0 | AFT survival regression | 3 | 5 | 6.2.4, 4.4.2 | Censoring convention verified; model fits | T19 | Y | Not started | 0%
6.3.2 | 6.0 | Concordance evaluation | 2 | 5 | 6.3.1 | C-index >= 0.65 | T19 | Y | Not started | 0%
6.3.3 | 6.0 | price_gap ablation study | 2 | 5 | 6.3.2 | Delta concordance recorded either way | T19 | N | Not started | 0%
6.3.4 | 6.0 | Left-truncation sensitivity analysis | 1 | 5 | 6.3.3 | Both fits reported; divergence discussed | T19 | N | Not started | 0%
7.1.1 | 7.0 | Price-vs-days curve generator | 2 | 5 | 6.3.1 | Monotonicity test green | T20 | Y | Not started | 0%
7.1.2 | 7.0 | Optimal price selection (isotonic) | 2 | 5 | 7.1.1 | 3 worked examples for the report | T20 | N | Not started | 0%
7.1.3 | 7.0 | Mispricing / bargain alert table | 1 | 5 | 7.1.2 | Top-100 underpriced liquid listings | T20 | N | Not started | 0%
7.2.1 | 7.0 | Feature importance & partial dependence | 2 | 5 | 6.2.3 | Top-10 rent drivers named and explained | T21 | N | Not started | 0%
7.2.2 | 7.0 | Residual failure-mode analysis | 2 | 5 | 6.2.3 | Failure modes by district, band, source | T21 | N | Not started | 0%
7.2.3 | 7.0 | Interactive district map artefact | 2 | 5 | 7.1.3 | Clickable folium artefact | T21 | N | Not started | 0%
8.1.1 | 8.0 | Report 1 - Project Proposal (Sep 20) | 4 | 1 | 1.1.1, 1.1.2 | Submitted Sep 20 | T8 | N | Not started | 0%
8.1.2 | 8.0 | Report 2 - Data Tasks (Oct 4) | 6 | 3 | 4.x, 5.x | Submitted Oct 4; Spark justification evidenced | T16 | N | Not started | 0%
8.1.3 | 8.0 | Report 3 - Model & Results (Oct 18) | 6 | 5 | 6.x, 7.x | Submitted Oct 18 | T22 | Y | Not started | 0%
8.1.4 | 8.0 | Report 4 - Final Consolidated (Oct 25) | 3 | 6 | 8.1.1-8.1.3 | Consolidated; design changes explained | T24 | N | Not started | 0%
8.2.1 | 8.0 | Public repository, README, diagram | 2 | 6 | all | Public; no credentials in history | T23 | N | Not started | 0%
8.2.2 | 8.0 | Reproducibility verification | 1 | 6 | 8.2.1 | Clean checkout runs from README alone | T23 | N | Not started | 0%
8.3.1 | 8.0 | Capstone presentation deck (~15 slides) | 2 | 6 | 8.1.4 | ~15 slides built | T24 | N | Not started | 0%
8.3.2 | 8.0 | Defence preparation & rehearsal | 1 | 6 | 8.3.1 | 4 questions answerable; rehearsed twice | T24 | N | Not started | 0%
|  | TOTAL - WORK PACKAGES | 150

## Roll-Up
Effort Roll-Up by WBS Branch
All values computed from the WBS Dictionary sheet - edit hours there, not here.
WBS | Element | Hours | % of Total | Packages | % Complete | Earned Hours
1.0 | Project Management & Governance | 10 | 6.061% | 8 | 0% | 0
2.0 | Data Collection System | 27 | 16.36% | 12 | 0% | 0
3.0 | Data Platform | 12 | 7.273% | 6 | 0% | 0
4.0 | Data Processing & Quality | 25 | 15.15% | 8 | 0% | 0
5.0 | Exploratory Data Analysis | 15 | 9.091% | 6 | 0% | 0
6.0 | Predictive Models | 25 | 15.15% | 10 | 0% | 0
7.0 | Results & Prescriptive Layer | 11 | 6.667% | 6 | 0% | 0
8.0 | Deliverables & Defence | 25 | 15.15% | 8 | 0% | 0
9.0 | Management Reserve (unallocated) | 15 | 9.091% | -
| TOTAL PROJECT EFFORT | 165 | 100% | 64 | 0% | 0
Management reserve is held against realised risk (see Risk Register), not scope growth.
Earned Hours = sum of (package hours x % complete). Update % Complete in the WBS Dictionary.

## Weekly Load
Weekly Effort Load vs Capacity
Capacity assumption (h/week) - editable: |  |  | 27
Week | Dates | Planned Hours | Capacity | Load % | Status | Key Milestone
0 | Pre-project (planning) | 6 | 0 | 0% | n/a | Charter, spec, WBS complete
1 | Sep 14 - Sep 20 | 34 | 27 | 125.9% | OVER | CRAWLER LIVE Sep 18; Report 1 Sep 20
2 | Sep 21 - Sep 27 | 30 | 27 | 111.1% | OVER | Spark cluster up; COHORT FROZEN Sep 25
3 | Sep 28 - Oct 4 | 26 | 27 | 96.3% | OK | Event-rate checkpoint; Report 2 Oct 4
4 | Oct 5 - Oct 11 | 17 | 27 | 62.96% | OK | Rent model meets MAPE target
5 | Oct 12 - Oct 18 | 25 | 27 | 92.59% | OK | PANEL CENSORED Oct 12; Report 3 Oct 18
6 | Oct 19 - Oct 25 | 9 | 27 | 33.33% | OK | Report 4 + oral defence Oct 25
| Continuous (weeks 1-6, ~0.5 h/wk) | 3 |  |  |  | Risk review, progress log, robots.txt re-check
| Management reserve (unallocated) | 15
| TOTAL | 165
Load % = Planned / Capacity. "OVER" above 110%, "TIGHT" above 100%.
Week 1 is deliberately front-loaded: the crawler must be live by Sep 18 or survival labels are lost permanently.

## Critical Path
Critical Path - Zero-Float Work Packages
A day lost on any package below moves the project end date.
WBS ID | Work Package | Hours | Week | Depends On | Why it is critical
2.1.3 | Crawl frontier (SQLite, panel-aware) | 4 | 1 | 2.1.1 | Frontier is the prerequisite for any crawling at all.
2.2.2 | Scrapy spider - batdongsan | 6 | 1 | 2.1.3, 2.2.4 | HARD DEADLINE Sep 18. Observation window cannot be back-filled.
2.2.4 | S3 bronze batch writer | 2 | 1 | 2.1.1 | Without the writer, fetched pages are not persisted.
2.3.2 | Full cohort freeze, stratified (Sep 25) | 1 | 2 | 2.2.3 | Cohort freeze date sets the start of every survival duration.
2.3.3 | Daily liveness probe scheduler | 2.5 | 2 | 2.3.2 | 17 days of elapsed observation - cannot be compressed by effort.
2.4.1 | EC2 deployment & cron scheduling | 1 | 1 | 2.2.2 | Unattended cron is what makes collection continuous.
4.1.3 | Spark bronze->silver parse job | 5 | 2 | 4.1.2, 3.2.3 | Silver layer blocks dedup, panel, features and both models.
4.3.1 | MinHash LSH dedup & canonicalisation | 4 | 2 | 4.1.3 | Unmerged re-posts corrupt survival labels irreversibly.
4.4.1 | Panel fact table (listing x day) | 1.5 | 3 | 4.3.1, 2.3.3 | Panel assembly gates all survival work.
4.4.2 | Right-censored survival labelling | 1.5 | 3 | 4.4.1 | Labels must exist before any model can be fitted.
6.1.2 | Leakage-safe temporal split | 2 | 4 | 6.1.1 | Leakage guard - without it, all reported metrics are invalid.
6.2.4 | price_gap scoring across all listings | 1 | 4 | 6.2.3 | price_gap is the feature linking Stage 1 to Stage 2.
6.3.1 | AFT survival regression | 3 | 5 | 6.2.4, 4.4.2 | The headline model of Report 3.
6.3.2 | Concordance evaluation | 2 | 5 | 6.3.1 | Success criterion C-index >= 0.65 is measured here.
7.1.1 | Price-vs-days curve generator | 2 | 5 | 6.3.1 | Prescriptive output depends on it; Report 3 conclusion.
8.1.3 | Report 3 - Model & Results (Oct 18) | 6 | 5 | 6.x, 7.x | Graded deliverable with a fixed external deadline.
| TOTAL CRITICAL-PATH EFFORT | 44.5
Note: 2.3.3 consumes only 2.5 h of effort but 17 calendar days. Elapsed time, not effort, is the binding constraint.

## Read Me
WORK BREAKDOWN STRUCTURE
Vietnam Urban Rental Market Intelligence
Project | End-to-end big data capstone: crawl Vietnamese rental portals, process on Spark, model fair rent and time-on-market, deliver four reports and an oral defence.
Window | 2026-09-14 to 2026-10-25 (6 weeks). Solo execution. 165 hours total effort.
Owner | Nguyen (nguyenpnt4@fpt.com)
Source documents | 01-project-charter.md - scope and success criteria 02-technical-design-spec.md - architecture and schemas 03-implementation-plan.md - task detail (Plan Ref column maps here) 04-schedule-and-milestones.md - dates and go/no-go checkpoints 05-risk-register.md - risks feeding the management reserve 07-work-breakdown-structure.md - narrative version of this workbook
HOW TO USE
Cells you edit | Only the YELLOW cells. In 'WBS Dictionary' these are Status and % Complete (one row per work package). In 'Weekly Load' it is the capacity assumption in D2. Everything else is a formula and will recalculate on its own.
Status values | Not started / In progress / Blocked / Done. All rows ship as 'Not started' - that is the expected format, overwrite it as work proceeds.
% Complete | Enter as a percentage (0% to 100%). Roll-Up multiplies it by package hours to give Earned Hours, so partial progress is visible without any extra bookkeeping.
Adding work | Insert rows inside the existing data range so the SUMIF and SUMPRODUCT formulas expand with them. Adding a row below the TOTAL row will be excluded from every total.
CONVENTIONS
Blue text | A hardcoded input, entered by hand rather than calculated.
Yellow fill | A cell you are expected to fill in or maintain.
Red 'Y' | Zero-float package - on the critical path. See the Critical Path sheet.
Green fill | A calculated total.
ASSUMPTIONS
Capacity 27 h/week | Supplied by the project owner as realistic availability alongside other commitments. Editable in Weekly Load D2 - every load figure follows it.
Reserve 15 h (9%) | Held against realised risk (R-01 crawler delay, R-12 Oracle capacity, R-05 duplicate contamination, R-06 parser breakage), NOT against scope growth. 9% is thin for a project carrying two critical risks; this is acknowledged, and the pre-agreed cut list is the response when it runs out.
Effort estimates | Bottom-up, produced by the project owner and Claude during planning on 2026-09-11. No historical velocity data exists for this team of one, so these are judgement-based and should be re-baselined after Week 1 actuals.
Week 0 work | Charter, spec, governance policy and this WBS are already complete and are shown at zero capacity, so they do not inflate the six-week load.
Exclusions | Images/CNN features, Streamlit dashboard, Supabase serving layer, streaming ingestion, sale listings, social-media sources, Airflow, and transformer embeddings are OUT OF SCOPE. Starting any of them requires a documented change.